## Sheet1
Questions | Answers
The 12 principples of agile manifesto serve as guidelines for teams to follow | TRUE
Select all agile principles that emphasize on customer collaboration | Business people & developers, Welcome changing requirements
Select all the roles in Scrum | Product owner, development team, scrum master
Primary purpose of scrum sprint | To deliver potentially shippable product increment
Scrum atrifact to track work items and progress during sprint | sprint backlog
Primary goal of agile manifesto | To uncover better ways of developing software by doing and helping others do it
Match the agile principle to correct statement
Deliver working software frequently | Working software is the primary measure of progress
Business people and developers must work together daily | Most efficient and effective method : Face to face conversation
XP discourages pair prgramming | FALSE
User stories are primarily written from perspective of development team | TRUE
Primary purpose of prioritizing user stories | To focus on delivering the highest valu efeatures list
Principles of agile manifesto | Deliver working software frequently, Business ppl and developers must work together daily, welcoming changing requirements
XP primarily focus on | Emphasizing high quality code and ferquent releases
Components of a well structured user story | acceptance criteria, goal or need, user role
Which is NOT a four values of agile manifesto | Following a plan over responding a change
What is a user story in context of agile development | A brief, user-centric description of a software feature
Purpose of user story | To capture functional requirement from the user's perspective
Which manifesto value promotes customer collaboration over ocntract negottiation | Customer collaboration
Which best describes Scrum | Scrum is an agile framework for managing and developing products
Match the agile value with its principle
Individuals and interactions over processes and tools | build projects around motivated individuals
Customer collaboration over contract negotiation | Deliver working software frequently with shorter timescales
Which role is typically responsible for creating and maintaining user stories | Product owner
Agile method focuses on delivering working software frequently in iterations of 1-4 weeks | Scrum